## Sheet1
# | Epic | User Story | Priority | Ready to be planned | Planned Sprint | Status
1 | Create Account | As a user, I want to create an account to be able to browse restuarants. | High | Yes | 1 | Completed
2 |  | As a user, I want to create an account to be able to order food . | High | Yes | 1 | Completed
3 | View Restaurants | As a user, I want to be able to see all available restuarants within my home location. | High | Yes | 1 | Completed
4 |  | As a user, I want to see all avaliable offer or discounts on all restuarants. | Medium | No | 2 | In progress
5 | Search Restaurants | As a user, I want to be able to search for a specific restaurant. | High | Yes | 1 | Completed
6 |  | As a user, I want to be able to search any restaurants even if it is not available within my location. | Low | Yes | 3 | Completed
7 |  | As a user, I want to search for restaurant that have offers. | Medium | No | 2 | In progress
8 | View Menu | As a user, I want to be able to view restaurant menu. | High | Yes | 1 | Completed
9 | Add to Cart | As a user, I want to add food into my cart. | High | Yes | 2 | Completed
10 |  | As a user, I want to add multiply food items into my cart. | High | Yes | 2 | Completed
11 |  | As a user, I want to add multiply food items from different restaurant into my cart. | Medium | No | 4 | Not started
12 | Purchase | As a user, I want to have the option to pay with cash or credit card. | High | no | 3 | In progress
13 |  | As a user, I want to have the avalibality to track my food. | Medium | No | 5 | Not started
14 |  | As a user, I need to have the ability to chat with my food delivery personnal. | Low | No | 5 | In progress
15 | Restaurant views order | As a restaurant owner, I need to be able to see all ordered food. | High | Yes | 2 | Completed
16 |  | As a restaurant owner, I need to be able to set, modify, change food prices or avalibality. | High | No | 5 | In progress
17 | Restaurant marks order as delivered | As a resturant owner, I need a mark indicating that food has arrived. | High | Yes | 4 | In progress